## Bar
Activity Name | Start Date | End Date | Individual Responsible | Progress | Status
Event Planning | 2023-03-01 | 2023-03-15 | Project Manager | 20% | In Progress
Venue Selection | 2023-03-16 | 2023-03-20 | Venue Coordinator | 50% | In Progress
Speaker Recruitment | 2023-03-21 | 2023-03-25 | Marketing Team | 70% | In Progress
Agenda Creation | 2023-03-26 | 2023-03-30 | Content Team | 90% | In Progress
Marketing and Promotion | 2023-04-01 | 2023-04-15 | Marketing Team | 60% | In Progress
Registration and Ticketing | 2023-04-16 | 2023-04-20 | Registration Team | 40% | In Progress
Event Setup and Logistics | 2023-04-21 | 2023-04-25 | Event Management Team | 10% | Not Started
Event Execution | 2023-04-26 | 2023-04-30 | Event Management Team | 0% | Not Started
Post-Event Evaluation | 2023-05-01 | 2023-05-05 | Project Manager | 0% | Not Started